## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Instructions on how to run
Team Name | 2195-swen-261-12-c-Wizards
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass |  | Pass |  | Pass
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass |  | Pass |  | Pass
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass |  | Pass |  | Pass
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass |  | Pass |  | Pass
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass |  | Pass |  | Pass
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass |  | Pass |  | Pass
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass |  | Pass |  | Pass
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass |  | Pass |  | Pass
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass |  | Pass |  | Pass
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass |  | Pass |  | Pass
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass |  | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass |  | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass |  | Pass |  | Pass
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass |  | Pass |  | Pass
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass |  | Pass |  | Pass
As a Player I want to make a move so that I know whether my move is valid. | Given that I have made a valid move, when I view the game board, the move is shown and a message saying "Move is valid" appears on the info box. |  |  | Pass |  | Pass
| Given that I have made an invalid move, when I view the game board, the move is not shown and a message saying something like "Move is invalid" appears in the info box. |  |  | Pass |  | Pass
| Given that I have made a valid move, when I have moved my piece diagonally 1 space, the piece is at the spot I put it in. |  |  | Pass |  | Pass
| Given that I have made a valid move, when I have made a jump, the jump removes the piece I jumped over and put my piece in the correct spot. |  |  | Pass |  | Pass
| Given that I have made a valid move and there are more valid moves for me to do (such as jumping a second time), when I move the piece, the board shows the piece moving and a message saying "Move is valid" appears in the info box. |  |  | Pass |  | Pass
As a Player, I want to be able to undo a move so I can perform the best moves possible. | Given that I have made a move and it is reflected on the board, when I click on the Backup button, my previous move is undone. If multiple moves have been made, only the last move should be undone |  |  | Pass |  | Pass
| Given that I have not made a move, the Backup button is greyed out. |  |  | Pass |  | Pass
As a Player, I want to show my opponent the moves I have made so my opponent can respond to my moves. | Given that I have made a valid turn, when I click on the "Submit turn" button, I cannot modify my moves anymore and my opponent will be able to see what moves I made. |  |  | Pass |  | Pass
| Given that I have made zero valid moves, when I view the game board, the "Submit turn" turn button is greyed out. |  |  | Pass |  | Pass
| Given that I have made an invalid series of one or more valid moves (ex. Move up once and jump over another piece), when I click the submit button, the game should ask me to redo my moves. |  |  | Pass |  | Pass
As a Player I want to be able to resign from a game so I can end a game early | Given I am in a game that is in session, I should be redirected to the home page. I should still be signed in so I can play another game without having to sign in again. The game lobby should be deleted and the opposing player should also be brought back to the home page |  |  | Fail | BC, 4/9/20, Unable to resign properly (throws an error but the page does not update automatilcally) (Refreshing fixes it) | Pass
Pass
As a Player I would like my piece to be able to turn my piece into a King in order to follow the rules of American checkers | Given I have moved a piece to the opposite side of the board, my piece should become a King |  |  | Pass |  | Pass
| Given I made a jump to reach the end of the board, I should not be able to king my piece and then make another jump on that same turn |  |  | Pass |  | Pass
As a Player, I want to be able to end the game according to the rules so I can either win or lose the game | Given I have removed all of my opponent's pieces and retained some of my pieces, when I view the gameboard, a message saying that I have won should be in the info box, and an Exit button should appear for me to exit the game |  |  | Fail | AP, 4/9/20 When the game is finished it redirects the user too many times | Pass
| Given that my opponent has won the game, when I view the gameboard, there should be a message saying I have lost, and an Exit button should appear for me to exit the game. |  |  | Fail | AP, 4/9/20 When the game is finished it redirects the user too many times | Pass
As a Spectator, I want to be able to spectate an ongoing game | Given that I have signed in, when I see the home page, I want to see a mean to select a game I want to spectate |  |  |  |  | Pass
| Given that I have signed in and selected a game to spectate, when I see the game, I want to be able to see the current state of the game and observe the changes from that moment onward |  |  |  |  | Pass
| Given that I am spectating a game, when I clicked on the Exit button, I want to be redirected to Home Page to either spectate another game or play a game |  |  |  |  | Pass